## Sheet1
Q&A FOR PROJECT TICKET VENDOR MACHINE
Project Manager: Nguyen Thien Huy
Project Duration: from 1 Ferbuary to 19 March
No. | Question | Answer | Created By | Created Date | Answer Date | Question Type | Status | Note
1 | Can a customer buy more tickets with different destination |  | Thien Huy | 18/3/2023 |  | Confirmation | Open
2 | Can a customer cancel and get their money back if they already bought a ticket |  | Thien Huy | 18/3/2023 |  | Confirmation | Open
3 | Can the system warning when the customer choose uncommon destination |  | Thien Huy | 18/3/2023 |  | Confirmation | Open
4 | How should the system respond and change the payment path when customer input invalid credit card |  | Thien Huy | 18/3/2023 |  | Clarification | Open
5 | What happens if the customer forget to take the credit card out |  | Thien Huy | 18/3/2023 |  | Clarification | Open
6 | Should the system have a postpaid ticket for regular customer |  | Thien Huy | 18/3/2023 |  | Confirmation | Open
7 | Can a customer have a button to contact with staff when they have problem |  | Thien Huy | 18/3/2023 |  | Confirmation | Open
8 | What happens if the system error and can't issue the ticket |  | Thien Huy | 18/3/2023 |  | Clarification | Open
9 | If the customer want to reserve the ticket, how should the system respond and implement |  | Thien Huy | 18/3/2023 |  | Clarification | Open
10 | What happens if the customer can't scan the QR code because of broken camera and try to pay with digital wallet |  | Thien Huy | 18/3/2023 |  | Clarification | Open